## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Siddartha Galla | 2026-08-29 | PDF document parser throws UnicodeDecodeError on non-standard encoding | Sprint 1 | Siddartha Galla | Standards | Added chardet auto-encoding detection and UTF-8 normalization | 2026-08-30 | Closed | Fixed in document_parsers.py
2 | Siddartha Galla | 2026-09-01 | Recursive chunker creating empty chunks on consecutive newline characters | Sprint 1 | Siddartha Galla | Logical | Filtered out whitespace-only chunks in text cleaner | 2026-09-01 | Closed | Resolved in text_cleaner.py
3 | Siddartha Galla | 2026-09-03 | Vector store search returns non-numeric NaN similarity score when query vector norm is 0 | Sprint 1 | Siddartha Galla | Logical | Added zero-norm division guard in cosine calculation | 2026-09-03 | Closed | Fixed in chroma_indexer.py
4 | Siddartha Galla | 2026-09-11 | Comparative query classification failing on 'Plan A vs Plan B' queries | Sprint 2 | Siddartha Galla | Logical | Added 'vs' and 'versus' regex patterns in QueryUnderstandingAgent | 2026-09-12 | Closed | Fixed in query_understanding_agent.py
5 | Siddartha Galla | 2026-09-14 | Stop words 'what', 'the', 'for' inflating keyword boost score on unrelated chunks | Sprint 2 | Siddartha Galla | Standards | Filtered English stop words in keyword boost calculator | 2026-09-14 | Closed | Fixed in chroma_indexer.py
6 | Siddartha Galla | 2026-09-15 | Response generation agent omitting citation IDs on multi-chunk responses | Sprint 2 | Siddartha Galla | User Interface | Appended citation pills [1], [2] to response text | 2026-09-15 | Closed | Fixed in response_generation_agent.py
7 | Siddartha Galla | 2026-09-25 | Vector similarity score drops to 0.00 across Python process restarts | Sprint 3 | Siddartha Galla | Logical | Replaced non-deterministic hash() with zlib.crc32 in embedder | 2026-09-25 | Closed | Fixed in embedder.py
8 | Siddartha Galla | 2026-09-26 | Web Speech STT recording icon remaining active after speech recognition ends | Sprint 3 | Siddartha Galla | User Interface | Added onend event handler to reset mic state | 2026-09-26 | Closed | Fixed in app.js
9 | Siddartha Galla | 2026-09-27 | Text-to-Speech TTS playback audio overlapping when Play button clicked multiple times | Sprint 3 | Siddartha Galla | User Interface | Added window.speechSynthesis.cancel() prior to new utterance | 2026-09-27 | Closed | Fixed in app.js
10 | Siddartha Galla | 2026-09-28 | Coreference resolution substituting pronoun 'its' with incorrect noun phrase | Sprint 3 | Siddartha Galla | Logical | Preserved multi-token capitalized plan names in entity extraction | 2026-09-28 | Closed | Fixed in memory_agent.py
11 | Siddartha Galla | 2026-09-29 | Evidence Inspector accordion overflowing on long chunk text previews | Sprint 3 | Siddartha Galla | User Interface | Added text wrapping and CSS max-height with scrollbar | 2026-09-29 | Closed | Fixed in styles.css
12 | Siddartha Galla | 2026-10-01 | REST API endpoint /api/ingest returning 500 error on empty file upload | Sprint 3 | Siddartha Galla | Standards | Added file size verification check before parsing | 2026-10-01 | Closed | Fixed in main.py
13 | Siddartha Galla | 2026-10-03 | Benchmark validation suite reporting false rejection error on out-of-bounds queries | Sprint 3 | Siddartha Galla | Logical | Adjusted rejection threshold evaluation criteria in test suite | 2026-10-03 | Closed | Fixed in evaluate_retrieval.py
14 | Siddartha Galla | 2026-10-04 | Domain filter dropdown in UI limiting user selection to Healthcare/Finance | Sprint 3 | Siddartha Galla | User Interface | Added dynamic domain sync from indexed database documents | 2026-10-04 | Closed | Fixed in app.js
15 | Siddartha Galla | 2026-10-06 | Unindexed general questions returning generic low confidence warning | Sprint 3 | Siddartha Galla | Logical | Added dynamic synthesis engine for unindexed open queries | 2026-10-06 | Closed | Fixed in response_generation_agent.py

## Sheet2
Logical
User Interface
Maintainability
Standards
Others